## Rakib
SL | Issue | Module | Work for | Type | Category | Priority | Status | Issue Date | Assign Date | Expected Resolution Date | EOD | Resolution Date | Raised By | Comments
1 | Branch, Department, Division etc Terminate Option. | Real Estate | Junaed |  | Out of scope | Medium | New | 2013-09-21 |  |  | 2013-10-03 |  | Prime Bank
2 | Branch, Department, Division Shifting Option. | Real Estate | Junaed |  | In scope | High | New | 2013-09-21 |  |  | 2013-10-03 |  | Prime Bank
3 | Purchase price, rent, advance money can change after agreement but before agreement period start. | Real Estate | Junaed |  | Out of scope | Medium | New | 2013-09-21 |  |  | 2013-10-03 |  | Prime Bank
4 | Rent enhancement by breaking agreement | Real Estate | Junaed |  | Out of scope | Medium | New | 2013-09-21 |  |  | 2013-10-03 |  | Prime Bank
5 | Some Dropdown Value Will be add | Real Estate | Junaed |  | In scope | Normal | New | 2013-09-21 |  |  | 2013-10-03 |  | Rakib islam
6 | Cash in counter name will be change to cash on counter | Insurance | Touhid |  | In scope | High | Done | 2013-09-21 |  |  | 2013-10-03 |  | Prime Bank
7 | Route will be shown auto for particular branch. | Insurance | Touhid |  | In scope | High | New | 2013-09-21 |  |  | 2013-10-03 |  | Prime Bank
8 | New rebate option needed. (For vehicle insurance only) | Insurance | Touhid |  | Out of scope | Medium | New | 2013-09-21 |  |  | 2013-10-03 |  | Prime Bank
9 | Locker Insurance is not 100% done | Insurance | Touhid |  | In scope | High | Done |  |  |  | 2013-10-03 |  | Rakib islam
10 | Asset Insurance is not 100% done | Insurance | Touhid |  | In scope | High | Done |  |  |  | 2013-10-03 |  | Rakib islam
11 | Printing Stationary and Security Insurance is not 100% done | Insurance | Touhid |  |  | High | Done |  |  |  | 2013-10-03 |  | Rakib islam
12 | IT Equipment's Insurance is not 100% done | Insurance | Touhid |  | In scope | High | Done |  |  |  | 2013-10-03 |  | Rakib islam
13 | Vehicles Insurance is not 100% done | Insurance | Touhid |  | In scope | High | Done |  |  |  | 2013-10-03 |  | Rakib islam
14 | Safety and Security is not 100% done | Safety and Security | Touhid |  | In scope | High | New |  |  |  | 2013-10-03 |  | Rakib islam
15 | After office note approval, Visite report will also go for approval | Civil & Electro | Touhid |  | In scope | High | New | 2013-09-14 |  |  | 2013-10-03 |  | Prime Bank
16 | In new requisition edit page user can’t edit product, without removing existing product. | for all | Rajib |  | In scope | High | New | 2013-09-21 | 2013-10-02 | 2013-10-03 | 2013-10-03 |  | Rakib islam
17 | Should have a comment field on good receive page. | for all | Rajib |  | In scope | High | New | 2013-09-21 | 2013-10-02 | 2013-10-03 | 2013-10-03 |  | Rakib islam
18 | Expiry date field needed when user receive a Safety product from good receive | Safety and security | Touhid |  | In scope | High | New |  |  |  | 2013-10-03 |  | Rakib islam
19 | Billing of Cash insurance will be process by motizil mother branch not by FAD | Insurance | Rajib |  | Out of scope | Medium | New | 2013-09-21 | 2013-10-02 |  | 2013-10-03 |  | Prime Bank
20 | Approval Process for vehicle accident, maintenance ETC | Transport Management | ahsan |  | In scope | High | New |  |  |  | 2013-10-03 |  | Rakib islam
21 | Vehicle Disposal is not ready yet | Transport Management | Touhid |  | In scope | High | New |  |  |  | 2013-10-03 |  | Rakib islam
22 | Suspense Requisition in not ready yet | for all | Rajib |  | In scope | High | New |  | 2013-10-02 |  | 2013-10-03 |  | Rakib islam
23 | Export option for Visiting Card (PDF and WS)
24 | Visiting Card approval process in not ready | Printing and Stationary | Touhid |  | In scope | High | New | 2013-09-12 |  |  | 2013-10-03 |  | Prime Bank
25 | Non MICR Product receive by maintaining product serial number is not ready yet | Non MICR | Rajib |  | In scope | High | New | 2013-09-12 | 2013-10-02 |  | 2013-10-03 |  | Prime Bank
26 | Non micr product send to user from store by maintaining product serial number is not ready yet | Non MICR | Rajib |  | In scope | High | New | 2013-09-12 | 2013-10-02 |  | 2013-10-03 |  | Prime Bank
27 | MICR Order data upload in pending | MICR | Shuvo |  | In scope | High | New |  |  |  | 2013-10-03 |  | Rakib islam
28 | Search by account number option will added on uploaded_data page | MICR | Shuvo |  | In scope | MEDIUM | New | 2013-09-11 |  |  | 2013-10-03 |  | Prime Bank
29 | Some report is not complete as per requirement format | MICR | Shuvo |  | In scope | High | New |  |  |  | 2013-10-03 |  | Prime Bank
30 | Real estate requisition and requisition approval peocess is not comolete | Real Estate | Junaed |  | In scope | High | New |  |  |  | 2013-10-03 |  | Prime Bank
31 | Officer can return requisition for any query to user | Electromechanical | Rajib |  | In scope |  | New | 2013-10-01 | 2013-10-02 | 2013-10-05 | 2013-10-03 |  | Prime Bank
32 | Deligation authority some times gives query or change the proposal/proposed vendor | Electromechanical | Rajib |  | In scope |  | New | 2013-10-01 | 2013-10-02 | 2013-10-06 | 2013-10-03 |  | Prime Bank
33 | Consultant add option needed and Consultant should be provision for approval,PO as well as Billing Procedure | Civil & Electro | Rajib |  | Out of scope |  | New | 2013-10-01 | 2013-10-02 | 2013-10-10 | 2013-10-03 |  | Prime Bank
34 | Multiple CS create option needed | Civil & Electro | Rajib |  | In scope |  | New | 2013-10-01 | 2013-10-02 | 2013-10-22 | 2013-10-03 |  | Prime Bank
35 | When user create a new requisition for pool car, car list will be not shown | Transport Management | Junaed |  | In scope | High | New | 2013-10-01 |  |  | 2013-10-03 |  | Prime Bank
36 | After division head approve Cost approval note will go tender comity with full CS info for recommendation ( IF open tender) | for all | Rajib |  | In scope | MEDIUM | New | 2013-10-01 | 2013-10-02 |  | 2013-10-03 |  | Prime Bank
37 | Line manager or division head can assign the requisition work to another officer at any stage | Civil & Electro | Touhid |  | In scope | High | New | 2013-10-01 |  |  | 2013-10-03 |  | Prime Bank
38 | 3 types of BOQ needed 1.st only product list 2nd Product list with Quantity 3rd Product + Quantity with price. | Civil & Electro | Touhid |  | Out of scope | Medium | Done | 2013-10-01 |  |  | 2013-10-03 |  | Prime Bank
39 | There should be provision for preparation of Bill of Quantity and Budget along with tender document | Civil & Electro | Touhid |  |  |  | New | 2013-10-01 |  |  | 2013-10-03 |  | Prime Bank
40 | All the Stack Holders shall informed the every steps of progress of the respective job | Civil & Electro | Touhid |  | Out of scope | High | New | 2013-10-01 |  |  | 2013-10-03 |  | Prime Bank
41 | There should have option for negotiation with any and/or all the participating bidder(s) against any tender | Civil & Electro | Rajib |  | In scope | High | New |  | 2013-10-02 | 2013-10-23 | 2013-10-03 |  | Prime Bank
42 | Add premium amount field on Cash in safe | Insurance | Touhid |  | In scope | High | Done | 2013-10-01 |  |  | 2013-10-03 |  | PB & Rakib
43 | Add premium amount field on Cash on counter. | Insurance | Touhid |  | In scope | High | Done | 2013-10-01 |  |  | 2013-10-03 |  | Prime Bank
44 | Propose route option needed | Insurance | Touhid |  | Out of scope | Medium | New | 2013-10-01 |  |  | 2013-10-03 |  | Prime Bank
45 | Payment will be made for cash related insurance through Motijheel Branch | Insurance | Touhid |  | Out of scope | Medium | New | 2013-10-01 |  |  | 2013-10-03 |  | Prime Bank
46 | Pending list will be shown and after receive the Pay Order regarding insurance rebate/commission of respective insurance policy, those be informed to Management for approval and depositing the same to Employees Welfare Fund A/C through FAD | Insurance | Touhid |  | Out of scope |  | New | 2013-10-01 |  |  | 2013-10-03 |  | Prime Bank
47 | CN no and bill amount may be added after receiving the respective courier CN. | Insurance | Dispatch |  | In scope |  | New | 2013-10-01 |  |  | 2013-10-03 |  | Prime Bank
48 | Bill payment for Dispatch in not ready | Insurance | Dispatch |  | In scope |  | New | 2013-10-01 |  |  | 2013-10-03 |  | Prime Bank
49 | In manage product menu, product will show requisition wise and product wise also | Civil & Electro | Rajib |  | Out of scope | Medium | New | 2013-10-01 | 2013-10-02 | 2013-10-24 | 2013-10-03 |  | Prime Bank
50 | Approval person can view approve requisition list, which are approve by him self | Civil & Electro | Rajib |  | In scope | High | New | 2013-10-02 | 2013-10-02 | 2013-10-25 | 2013-10-03 |  | Prime Bank
51 | In manage product menu, Reorder level will be also shown | Printing stationary | Rajib |  | In scope | High | New | 2013-10-01 | 2013-10-02 | 2013-10-27 | 2013-10-03 |  | Prime Bank
52 | Search option is not working properly (manage_product/evaluations.php) | All | Rajib |  | In scope | High | New | 2013-10-01 | 2013-10-02 | 2013-10-28 | 2013-10-03 |  | Rakib islam
53 | Previous CS are not showing. | All | Rajib |  | In scope | High | New | 2013-10-01 | 2013-10-02 | 2013-10-28 | 2013-10-03 |  | Rakib islam
54 | Without selecting any vendor Officer Shouldn’t Process the CS | All | Rajib |  | In scope | High | New | 2013-10-01 | 2013-10-02 | 2013-10-29 | 2013-10-03 |  | Rakib islam
55 | Officer should have view only those PO which are related with him/her process department | All | Rajib |  | In scope | High | New | 2013-10-01 | 2013-10-02 | 2013-10-28 | 2013-10-03 |  | Rakib islam
56 | Search option is not working properly (po/workorders_list.php) | All | Rajib |  | In scope | High | New | 2013-10-01 | 2013-10-02 | 2013-10-29 | 2013-10-03 |  | Rakib islam
57 | From date – to date field should be blank first. User will set From date – To date | All | Rajib |  | In scope | High | New | 2013-10-01 | 2013-10-02 | 2013-10-29 | 2013-10-03 |  | Rakib islam